## eBase
eBase Development
Story ID | Phase | Objective | User Story | MoSCoW | Users | Business | Success criteria | Estimate | Min | Max | Comment
1 | 2 | Call centre | Banned list tracking | Must |  | As a business I want to be able to record a users banned history in order to track the banned reasons and periods | Ability to record the following ban history in the Call centre edit permit details screen for HCC staff only (banned users cannot use their permit and do not recieve automated emails): 1. Start date of ban 2. End date of ban 3. Tick boxes reason for ban (allowing for multiple selections): Abusive behaviour, Commercial/trade waste, Site policy abuse and Fly-tipping 4. Automatically record the name of the HCC staff member that applied the ban based on log in details (email username?) 5. Display these additional fiels in the call centre view permit details screen 6. Operative system view permit details screen to display red warning message that the permit user is banned and accept button to be hidden so operative cannot accept their visit | 2 -2.5 days | 2 | 2.5 | YES
2 | 2 | Call centre | Deactivate permit | Must |  | As a business I want to be able to temporarily deactivate a permit in order to retain the details of the permit while preventing the user from using the permit | Ability to deactivate a permit for a period of time in the call centre edit permit details screen- deactivated permits should be treated the same as banned permits (users cannot use their permit and do not receive automated emails): 1. Button to deactivate permit 2. When deactivated button to reactivate permit (in place of deactivation button if possible) 3. Automatically record start date and end date of deactivation 4. Tick box reason for deactivation (allowing for multiple selections): Change of residence, Change of Vehicle, Change of name, Change of circumstances, Change of email and Administrative query 5. Automatically record the name of the staff member that applied the ban based on log in details (email username?) 6. Display these additional fields in the call centre view permit details screen 7. Deactivated permits will need to be missed from validation checks for issuing new permits- namely household, email and vehicle registration checks (until/if reactivated again) 8. Operative system view permit details screen to display red warning message that the permit is deactivated and accept button to be hidden so operative cannot accept their visit | 2-3 days | 2 | 3 | YES
24 | 2 | Call centre | Download refusal photos | Could |  | As a business I want to be able to easily download the refusal photos from the database in order to access the evidence for refusal | Ability to easily download refusal photos from the database: 1. Each photo to be provided with corresponding permit number, date of refusal and reason for refusal 2. Two report options- one to report on all refusal photos against a permit number between a start and end date and one to report on all refusal photos against one or all HWRC's between a start and end date 3. Ability to export and save the refusal photo report | 2-2.5 days
20 | 2 | Call centre | Report on call centre staff that issued the permit | Must |  | As a business I want to be able to report on the call centre staff that issued the permit in order to manage staff redirecting users to self-serve their permit | Ability to report on call centre staff that issue the permits 1. Add email username of call centre staff that issued the permit to the all current permits, all expired permits, and all data reports | 0.5 day | 0.5 | 0.5 | YES
19 | 2 | Call centre | Record permits issued by the call centre | Must |  | As a business I want to be able to record the name of the call centre staff that issued the permit in order to know which permits and who issued from the call centre or permits obtained via self-service | Ability to automatically record the name of the call centre staff member that created the new permit (not permit amendments) based on log in details (email username)? | 0.5 day | 0.5 | 0.5 | YES
18 | 2 | Call centre | Resend permit email | Must | As a user I want the business to be able to resend my permit email in order to receive my permit | As a business I want to be able to resend the permit email to users that have not received or accidentally deleted it in order for users to receive their permit | Ability to resend users their permit email in the call centre permit details screen: 1. Button to resend permit email to the user- with remaining visits | 0.5 day | 0.5 | 0.5 | YeS
3 |  | Database | Automated process- record and track visits (ANPR) | Won't |  | As a business I want the HWRC to automatically record and track use of the van permit to automate the process and reduce costs | The following information will need to be recorded for each visit: vehicle registration, image of vehicle, location of visit (HWRC), date and time of each visit. Visit information will have to tally with the users details and be recorded in a database to keep track of all visists. Also all vehicle visits will need to be recorded in order to enforce the permit process for citizens that have not used the van permit to dispose of items at the HWRC
4 |  | Database | Service informed | Won't |  | As a business I want to be informed when a user attempts to exceed their number of visits or visits an HWRC after their permit has expired so that the HWRC can enforce the process and challenge the user/citizen | Method to inform the business immediately and provide the detail in order to challenge the user/citizen: permit number (unique ID), user issued to (name), user contact details (mobile, address and email), vehicle type (van, truck, trailer), own vehicle/trailer or hire vehicle/trailer, vehicle make/model/registration (if owned), email/paper permit, permit expiry date, number of visits (within permit), renewal/first issue permit, location of each visit (HWRC), date and time of each visit.
5 |  | Database and User Form | Automated address verification | Won't |  | As a business I want the users address to be verified automatically against their council tax number in order to prevent misuse of the process | As the new process is providing permits via email users could enter any address in order to apply for another permit so it would be helpful if the process could automatically verify a users address is correct before issuing the permit. While this isn't something that we may wish to do intially it is important that the solution has the ability to integrate should it be required in the future.
6 | 2 | Operatives | HWRC Search | Must | As a user I want HWRC staff to be able to search for my permit by postcode or vehicle registration if I forget to bring it to the HWRC so that I can use a van to dispose of items at the HWRC | As a business I want HWRC staff to be able to search for users permits by postcode or vehicle registration if they forget to bring it to the HWRC so that they can use a van to dispose of their items at the HWRC | Ability for the HWRC operatives to search by postcode to find the address or vehicle registration to find the vehicle: 1. Search field for vehicle registration 2. Search field for post code 3. List of search results for operatives to select the correct permit 4. Search to work similarly to call centre search and provide similar results (call centre search works well to provide closest match) | 1-1.5 day | 1 | 1.5 | YES
7 | 3 | Operatives | QR Code | Must | As a user I want the operatives to be able to quickly register my visit so I can dispose of my household waste at the HWRC | As a member of Amey staff I want to easily scan a QR code to automatically find the permit (rather than type in the number) in order to prevent mistakes and save time at the HWRC | Ability to generate a QR code for each permit so operatives can scan to record visits on their devices instead of typing in permit number: 1. Ability to generate unique QR code for each new permit 2. QR code to be scanned by operative to automatically record visits against unique permit number 3. QR code to be provided clearly on the automated permit email 4. QR code to be added onto automated permit amendment email (from both public and call centre systems) to increase proportion of users with QR codes 5. QR code to be added to resent permit emails (from call centre system) 6. QR code to be scanned from a device (digtially) or printed permit by the operatives 7. Scan QR button to be added to the top of the operative system search screen 8. Failure to find the permit using the QR code requires a message to inform operative that the permit could not be found and take the operative back to the search screen so they can either | 5-7 days | 5 | 7 | YES
8 | 2 | Operatives | Display previous visits & refusals | Must |  | As a business I want to display the users previous visits and refusals to the operatives in order to provide them with the information they need to decide to accept or refuse their visit | Ability to display history of visits and refusals to operatives when accepting/refusing a visit in the operatives permit details screen (under the current information in the screen): 1. List all recorded visits and refusals against the current (12 month) permit 2. Accepted visits to include: HWRC visited, date of visit and all types of waste 3. Refused visits to include: HWRC visited, date of visit and reason for refusal | 1-1.5 days | 1 | 1.5 | YES
21 | 2 | Operatives | Notify HWRC's of refusals | Should |  | As a business I want to the system to automatically notify HWRC's when a user is refused a visit in order to flag potential misuse of the permits | Ability to send automated notification email to all HWRC's when a users visit is refused Email notification to inlcude the following: Permit number, title, first name, surname, address, postcode, vehicle type, own/hired, vehicle make, vehicle model, vehicle registration, HWRC visited (automated using email username), time of visit and reason for refusal | 0.75 day | 0.75 | 0.75 | Could use WhatsApp instead
23 | 3 | Operatives | Photo upload for refusals | Could |  | As a business I want to be able to upload a photo of the waste the user is attempting to dispose for each refusal in order to evidence reason for refusal | Ability to upload one photo of waste the user is attempting to dispose for each refusal: 1. Ability to use mobile device to capture one photo 2. Ability to find the photo on the mobile device 3. Ability to upload the photo to the system to be stored in the database against the refusal 4. Photo file size to be reduced to a managable size for the database | 3-6 days
9 | 2 | Operatives | Record reason for refusal | Must |  | As a business I want the operatives to record the reason for refusal of a visit, HWRC site and date of refusal in order to track refusals | Ability for operatives to select reason for refusal and date (if back dated refusal): 1. New screen required when operative clicks reject in the permit details screen 2. New screen to record reason for refusal (drop down) and date (if a back dated refusal) 3. If date (for back dated visit) not entered (or today/future date entered) to automatically record date and time of rejection in the database 4. Reason for refusal drop down to include (one selection allowed): Too much Construction & Demolition waste , Too much plasterboard (also C&D waste), Abusive behaviour, Suspected commercial/trade waste, Site policy abuse and Incorrect permit presented. 5. Ability to automatically capture the HWRC using the email username 6. The reasons for refusal, HWRC and date of refusal (automated if blank/back dated if provided) to be recorded in the database | 1-1.5 days | 1 | 1.5 | YES
25 | 2 | Operatives | Report on reason for refusal | Must |  | As a business I want to be able to report on the reasons for refusal inlcuding the HWRC site and date in order to track refused visits | Ability to report on the reasons for refusals, HWRC site and dates of refusals: 1. Add the reason for refusal, HWRC site and date of refusal to the all visits and all data reports | 1-1.5 days | 1 | 1.5 | YES
22 | 2 | Operatives | Send alerts to HWRC's | Should |  | As a business I want to be able to send an alert to HWRC's following user abuse in order to warn other HWRC's | Ability to send alert to all HWRC's using drop down reason for alert and ability to link to a permit if posisble or capture vehicle registration if not 1. If possible link to permit in order to record in database and access information for notification email- alert button in operative system permit details screen 2. If not possible to link to permit (e.g. no permit or hire vehicle) ability to record vehicle registration- alert button in operative system search screen 3. Capture reason for alert from drop down options (one selection): Too much Construction & Demolition waste , Too much plasterboard (also C&D waste), Abusive behaviour, Suspected commercial/trade waste or Site policy abuse 4. Ability to automatically capture the HWRC using the email username 5. Ability to automatically capture the time and date of the alert 6. Send automated email to HWRC's informing them of the alert inlcuding the following: - Permit found: Permit number, title, first name, surname, address, postcode, vehicle type, own/hired, vehicle make, vehicle model, vehicle registration, HWRC visited, time of alert and reason for alert - Permit not found: Vehicle registration, HWRC visited, time of alert and reason for alert 7. Ability to save this information in the database for reporting purposes | 1.5-2 days
10 | 3 | Operatives | System log out | Must |  | As a business I want operatives to be able to log into the system at the start of the day and stay logged in for the day in order to save the operatives having to re-enter log in details | Ability for the operatives to stay logged into the system for two hours to save them having to regulary re-enter their log in details 1. Extend eBase automated time out from 1 hour to 2 hours | Investigate | 0.5 | 1 | I am told that this is now possible to do in Ebase v5
11 |  | User form | Change email | Won't | As a user I want to be able to change my email on my account in order to self-serve | As a business I want users to be able to change their email address on their account in order for them to self-serve | Ability for users to change their email address in their account
12 |  | User form | Charging for subsequent visits | Won't |  | As a department I want to be able to charge users for subsequent visits (once they have used their 12 visits per year) in order to generate income for the business | Ability for business to charge van permit users for subsequent visits if they require more than 12 visits a year.
13 | 2 | User form | Data validation | Must | As a user I want my information to be verified as it is entered into the system in order to prevent issues arising with my van permit application | As a business I need to ensure that the information entered into the system by the user is verified in order to prevent issues arising with their van permit | Ability to improve data collection by including the following data validation: First name- min 2 characters max 20 characters Surname- min 2 characters max 20 characters Post code- min 5 characters max 10 characters must be mixture of numbers and letters (call centre system manually entered address only) Phone number- min 5 characters max 25 characters can be mixture of numbers and letters Email- min 8 characters max 50 characters must contain @ and at least one full stop? Vehicle make- min 2 characters max 20 characters can be mixture of numbers and letters, cannot be same as model? Vehicle model- min 2 characters max 20 characters can be mixture of numbers and letters, cannot be same as make? Vehicle Registration- min 2 characters max 10 characters must be mixture of numbers and letters cannot be same as make or model? | 1.5-2 days | 1.5 | 2 | The new validation might not be exactly as requested because for example postcode and email both have some standard validation criteria - which is stricter than what you are suggesting.
14 | 3 | User form | Improved log in | Must | As a user I want to be able to log into my van permit account easily and securely in order to check how many visits I have remaining and amend my details | As a business I want users and the service to be able to easily and securely log in to their accounts in order to self-serve/use the system | Ability for users to easily and securely log in to their accounts with minimal issues: 1. Reduce requirement for manual intervention to resolve password/log in issues 2. Improve self-service ability for users to reset passwords and log in issues | Investigate |  |  | Ongoing
15 | 2 | User form | Monitor reapplications | Must |  | As a business I want to be able to view how users are reapplying for permits in order to monitor usage | Ability to record and report on how many permits a user has had and the start date of their first permit 1. Add total number of permits and start date of first permit to the banned list, all current permits, expired permits and all data reports | 0.5-0.75 day | 0.5 | 0.75 | YES
16 | 3 | User form | Multiple vehicles | Should | As a user I want to be able to upload multiple vehicles onto the permit so that I can use multiple vehicles to dispose of waste at the HWRC's | As a business I want users to be able to add mutliple vehicles onto their permit so they can use multiple vehicles to dispose of waste at the HWRC's | Ability for users to upload up to three owned vehicles onto their permit to enable them to use any of the three vehicles for each visit to the HWRC. Operatives will be able to check all three vehicle details against the vehicle that the user brings to the HWRC (on the operative portal): 1. In the public system register a new user account and edit details, call centre system to create a new permit and edit details- user that selects owned vehicle will have a button to add another vehicle 2. Button to add another vehicle will duplicate the vehicle make, vehicle model, vehicle registration and any distinguishing marks on vehicle fields to record another vehicle 3. User will then have the option to add a third vehicle using the same fields if required (but no more than three vehicles) 4. All of these vehicle registrations will have to be checked to ensure no duplicates in the database- duplicates will need to be rejected 5. Ability for users with a permit to log in to their account and add/edit up to three vehicles to their permit 6. Ability to delete up to two additional vehicles (down to one owned/hired vehicle) | 7-10 days | 7 | 10 | Too expensive- only two complaints
17 | 3 | User form | Improved password reset | Must | As a user I want to be able to reset my password if I forget it in order to log into my account quickly and easily | As a business I want users and the service to be able to reset their passwords if they forget in order to log into their accounts quickly and easily | Ability to quickly and easily reset their password in order to log in to their accounts | Investigate |  |  | Ongoing
26 | Done | Call centre | Amey call centre access to WASP | Must | As a user I want to be able to contact the Amey call centre to easily resolve my log in and email issues in order to continue using my permit | As a business I want Amey to be able to access WASP in order to deal with user log in issues and email changes in order to manage all user issues | Ability for Amey to access WASP in order to manage user log in issues and email changes
27 | 2 | Call centre | Reminder to check email address | Must | As a user I want to be reminded to check that the email I have entered is correct in order to receive my permit and be able to log in to the system | As a business I want to remind users to check their email address is correct to prevent issues with users not receiving their permit or being able to log in to the system | Ability to remind users to check their email address when applying for their permit 1. Add the following line above the email address field: Please check your email address is correct before 2. Investigate if user can be stopped from copying and pasting email to force them to retype | 0.5 - 1 day | 0.5 | 1 | I read that doing this is not really recommended and will not necessarily work on all platforms. That said, it is possible to make things more difficult for the user. To do so I would have to alter the call centre form because I'm sure they wouldn't want this annoying feature.
28 |  | Call centre | Backdate user visits and refusals | Must |  | As a business I want to be able to record backdated visits and refusals in the operative system in order to capture vists that could not be recorded at the time of the visit | Ability to record backdated visits and refusals in the operative system: 1. In the operative accept/reject visit screen, date field to back date visit- if required 2. If date entered to overwrite automated date of accepted/rejected visit 3. Ability to record this information in the database for reporting purposes 4. Ability to send automated visit email to the user- with back dated visit date 5. Automated email to be an adapted version of standard accepted visit email to highlight that it is regarding a back dated visit | 0.5-1 day | 0.5 | 1 | Yes
29 | 3 | Operatives | Delayed password reset | Must |  | As a business I want to delay the automated renewal of passwords as much as possible in order to avoid issues with the operatives logging into the system | Ability to delay the automated password renewal which has caused issues with operatives accessing the system | Investigate |  |  | Ongoing
30 | 2 | Call centre | Permit details to menu | Must |  | As a business I want to be able to return to the menu from the permit details screen in order to improve the call centre system navigation | Ability to click a back to menu button on the permit details screen to return straight to the menu screen | 0.1 day | 0.1 | 0.1 | Yes
31 | 2 | Call centre | Edit permit details to menu | Must |  | As a business I want to be able to return to the menu from the edit permit details screen in order to improve the call centre system navigation | Ability to click a back to menu button on the edit permit details screen to return straight to the menu screen | 0.1 day | 0.1 | 0.1 | Yes
32 | 2 | Call centre | Create new permit default to own vehicle | Must |  | As a business I want the create new permit screen own/hired drop down to default to owned vehicle as majority of applications are for owned rather than hired vehicles | Ability for the create new permit screen in public and call centre system own/hired drop down to default to owned vehicle | 0.3 day | 0.3 | 0.3 | Yes
35 | 2 | Operatives | Permit details to search | Must |  | As a business I want to be able to return to the search screen from the permit details screen in order to improve operative system navigation | Ability to click a back to menu button on the operatives system permit details screen to return straight to the search screen | 0.1 day | 0.1 | 0.1 | Yes
36 | 2 | Operatives | Automate HWRC selection based on email username | Must |  | As a business I want the system to automatically record the HWRC site based on the email username in order to save the operative selecting | Ability to automatically record the HWRC site based on the email username when accepting visits, rejecting visits and sending alerts | 0.5-0.75 day | 0.5 | 0.75 | Yes
33 | 2 | Call centre | All visits report date parameters | Must |  | As a business I want to be able to report on all visits between a start and an end date in order to limit the report out turn | Ability to enter a start and end date for the all visits report in order to report on all visits between two dates | 0.5 day | 0.5 | 0.5 | Yes
34 | 2 | Call centre | All data report date parameters | Must |  | As a business I want to be able to report on all data between a start and an end date in order to limit the report out turn | Ability to enter a start and end date for the all data report in order to report on all visits between two dates | 0.5 day | 0.5 | 0.5 | Yes
37 | 2 | Call centre | All visits report permit search | Must |  | As a business I want to be able to report on all visits against a permit number in order to limit the report out turn | Ability to enter a permit number for the all visits report in order to report on all visits against a specific permit | 0.5 day | 0.5 | 0.5 | Yes

## Devices
Devices
Story ID | Business/ Technical | User Story | MoSCoW | Operatives | Business | Success criteria
1 | Business | Weather resistant | Must | As an operative I want to be able to use the device in all weather conditions in order to administer the process |  | Water proof device which will also work in temperture extremes- heat of summer and cold of winter
2 | Business | Small and light | Must | As an operative I want the device to be as small and light as possible so I can have easy access to the device at all times |  | Either hand held device that will fit in the operatives pocket or a non-intrusive tablet case that can be carried on an operatives shoulder
3 | Business | Resilliant | Must | As an operative I want the device to be resillent enough to be knocked and dropped onto a hard floor without breaking |  | Case will have to be tough enough to withstand device being dropped from height onto hard floor and knocked
4 | Technical | Connect to the internet | Must | As an operative I need the device to connect to the internet at the HWRC in order to access the van permit system |  | Majority of the HWRC's have wi-fi although may also have to operate on 3G via a sim card (e.g. Cole Green)
5 | Technical | Compatible with the van permit system | Must | As an operative I need the device to access the van permit system so that I can administer the process | As a business I need the devices that the operatives have to access the van permit system so they can administer the process | It is important that the system works on the devices that the operatives have at the HWRC of course.
6 | Business | Lasting battery | Should | As an operative I want the battery to last so I can use the device all day without having to keep charging
7 | Technical | Use in all light levels | Should | As an operative I want to be able to see the screen in all light levels in order to administer the process |  | Screen will need to be visible in bright sun light (summer) or fading light levels (winter)
8 | Business | Use with thick gloves | Should | As an operative I want to be able to use the device while wearing thick gloves to save time removing and putting my gloves back on again |  | Explore using a stylus to operate with gloves- although case would have to incorporate stylus storage
9 | Business | Restricted use | Should |  | As a business I want to restrict what the devices can be used for in order to prevent missue of the devices | Potentially devices are only to be used for the van permit process- also reduces risk of device being a target for theives
10 | Technical | Camera | Should | As an operative I want to be able to scan a QR code to find the van permit rather than type in the permit number to speed up the process and prevent mistakes | As a business I want the van permit process to be as quick and accurate as possible at the HWRC's | Camera for QR code scan rather than typing in the permit number

## Issues
Issues Log
Number | Description | Further information | Status | Comment

## Feedback Log
Feedback log
Last updated
Feedback | Running total | Comments